Irish Rural Link Action Plan – under the SSNO programme

Overall Aim:

In relation to our Primary Strategic Priority

## Time frame – 2016 - 2019

| Primary Strategic Priority: Policy Development |
| --- |
|  | Objectives (SMART) | Actions | Outputs | Timeframe |
|  | Example: Build the capacity of organisations within the Community and Voluntary Sector in relation to corporate governance and financial management | Example: Deliver organisational development workshops | Example: Number of membership organisations or constituent bodies engaging in organisational development workshops on corporate governance and financial management |  |
| 1 | Represent the interests of disadvantaged rural communities through influencing policy | Secure and maintain representation of national consultative committees Secure and maintain representation on European consultative committees. Relay policy message through local, regional and national media. | A seat secured/retained on 10 no. of national fora. A seat secured/retained on 1 no. of EU fora. A minimum of 100 no. of press releases and radio interviews made per annum. | 2016,17,18 and 2019 |
| 2 | Research and formulate policy on sector rural issues of disadvantage. | Formulate and make policy submission on issues of relevance to disadvantaged rural communities. Develop Research papers on Rural issues that need to be addressed. | 12 no. written policy submissions made Research and document 4 no. of rural issues of relevance per calendar year Carry out survey and/or consultation events to feed into policy on 12 no. of issues per calendar year. | 2 in 2016, 4 in 2017, and 4 in 2018, 2 in 2019 |
| 3 | Act as an Advocate for rural areas and Provide a link between isolated and unheard rural communities and government | Run information sessions on policy issues to inform rural communities. Publish a newsletter online and in hard copy format. | 5 no. information sessions run annually. Quarterly newsletter published. | 2016 (4), 2017 (4), 2018(4) 2019 (2) |

## The timeframe should cover actions up until 30th June 2019.

| Secondary Strategic Priority: Organisation Development & Front Line service delivery |
| --- |
|  | Objectives (SMART) | Actions | Outputs | Timeframe |
| 1 | Build the capacity of rural organisations within the Community and Voluntary Sector in relation to corporate governance. | Deliver training courses and workshops in corporate governance | 6 no. of corporate governance workshop completed. 120 no of participants complete corporate governance training. | 1 in 2016 and 2 in 2017, 2 in 2018, 1 in 2019 |
| 2 | Work toward s making IRL a more self-sufficient and sustainable organisation. | Train regional voluntary membership/liaison development officers. Launch membership recruitment drive. Deliver governance and financial management training to board members. | 10 no. of volunteers trained as membership /liaison officers. 15 % increase in membership of groups and individuals. 15 no .of member groups trained in corporate governance. | 2016 - 2019 2019 completed |
| 3 | Investigate the development of a National Villages Network/representative body | Consult with village and community councils and develop a strategy for representation within IRL. | 4 national village’s representative body model developed. | By mid 2019 |
| 4 | Provide a nationwide service to government Departments and agencies to roll out policy. | Run information sessions to isolated rural communities nationwide. | 8 no. of national information campaigns undertaken. | 2016 - 2019 |